## Site audit
ID | URL | Page | Item | Type | Light | Proposed action | Depends on | Owner | Status | Source | Notes | Verified live
QA-001 | (global) | Header menu | Products > Infografix -> infografix.app (dead, redirects to quark.com) | Nav link | Red | Remove link | - | Vinodh | doing | call+scan | DEC-10. Due 21 Sep | 21 Sep live fetch: NOT done yet - infografix.app link still in header menu
QA-002 | (global) | Footer | Products > Infografix.app link with megamenu UTM | Nav link | Red | Remove link | - | Vinodh | doing | call+scan | DEC-10 | 21 Sep live fetch: NOT done yet - footer link with megamenu UTM still present
QA-003 | (global) | Header menu | QuarkXPress > 'What's New in QuarkXPress 2026' label | Year ref | Green | Rename to new release | MSG (name) | Vinodh | blocked | scan
QA-004 | (global) | Header menu | QuarkXPress Competitor Comparison -> content.quark.com/26_QXP_Features_Comparision_V22 | PDF asset | Yellow | New comparison PDF or keep with note | MSG; Q-08 owner of content.quark.com | TBD | open | scan | Filename carries 26 + V22
QA-005 | (global) | Header + footer | Developer SDK link -> developer.quark.com/july2025_v5/ | Link | TBD | Check if QPP-only; likely out of scope | - | Vinodh | open | scan | QPP, probably leave
QA-006 | (global) | Language switcher | ~40 languages listed | Localisation | TBD | Establish auto-translate vs hand-maintained | - | Vinodh | open | scan | Q-03. Could multiply every row below
QA-007 | (global) | Site-wide modal | 'Request a call' form: country, company revenue, 2 consents | Form | TBD | Confirm where it submits; no release change expected | - | Vinodh | open | scan | Appears on every scanned page
QA-008 |  | Homepage | Hero / slider - currently generic 'AI-Powered Enterprise Content and Desktop Publishing Software' | Hero | Yellow | Release slide per design A-03 | MSG; A-03 | Design + Vinodh | blocked | call+scan | Flagship
QA-009 |  | Homepage | QuarkXPress block: Free Trial + Buy Now (utm bannerQXP) | CTA | Green | No change - block names no version | - | Vinodh | no action | scan |  | 21 Sep live fetch: block names no version or year
QA-010 |  | Homepage | Infografix block: 'Create Infographics in Seconds...' + 'get started' -> infografix.app | Module | Red | Remove block (dead product, dead link) | Andrew OK | Vinodh | open | scan | Not raised on call. DEC-10 keeps pages, but this is a homepage promo for a dead link | 21 Sep live fetch: confirmed - block live, 'get started' -> infografix.app
QA-011 |  | Homepage | QuarkXPress testimonial - 'Jason C, Creative Imagineer' | Reviews | Orange | Keep / refresh / drop | Q-07 | Andrew | open | scan
QA-012 |  | Homepage | Awards strip: FTC 2024, Gold Winner 2023, Great Place to Work 2023-2024, KMWorld, ISO 27001 | Module | Orange | Trim dated badges | Andrew OK | Zamstars | open | scan | Not release-critical | 21 Sep live fetch: confirmed - FTC 2024, Gold Winner 2023, GPTW US 2024, GPTW UK 2023, Best Workplaces 2023
QA-013 | (global) | Footer (site-wide) | G2 reviews link | Reviews | TBD | Check it resolves + rating is current | - | Zamstars | open | scan |  | Not checked - G2 blocks automated fetch. Link sits in the site-wide footer, not only the homepage. Needs a human click
QA-014 |  | QXP product page | Hero with pricing toggle (Annual Subscription / Perpetual License) | Hero | Yellow | New hero per design A-02 | MSG; A-02 | Design + Vinodh | blocked | call+scan | Flagship
QA-015 |  | QXP product page | All 'QuarkXPress 2026' mentions (multiple) | Year ref | Green | Swap to new release name | MSG (name) | Vinodh | blocked | scan
QA-016 |  | QXP product page | Feature showcase: Variable Fonts, Math Equations, Quarky AI, Paste Into, Font Pairing, Paper Color Previews | Feature list | Yellow | Replace/reorder from master features list F-01 | MSG; F-01 | Design + Vinodh | blocked | scan
QA-017 |  | QXP product page | 6 per-feature YouTube videos + 1 overview (youtu.be/5l54uqfpg1c) | Video | Orange | Drop per-feature videos for new features; screenshots instead. Overview video: replace or remove | Q-06; Q-11 screenshots; F-04 | Design -> Andrew | open | call+scan | DEC-09
QA-018 |  | QXP product page | CTA 'See everything new in QXP 2026' -> whats-new page | CTA | Green | Relabel | MSG (name) | Vinodh | blocked | call+scan | Andrew named this one on the call
QA-019 |  | QXP product page | Reviews: 4 Gartner snippet iframes + Capterra logo + Martin Turner quote | Reviews | Orange | Test embeds; fix, re-source or switch off now | Q-07 | Vinodh -> Andrew | open | call+scan | Likely the 'broken reviews' from the call. DEC-14 allows acting now. Ready-made replacement exists: see QA-070 | 21 Sep live fetch: host datainsights-cdn.dm.aws.gartner.com does not resolve in DNS from two separate networks (gartner.com does). Dead for every visitor, not a scraper artefact
QA-020 |  | QXP product page | System requirements: macOS 26/15/14, Windows 11/10 | Spec | Yellow | Update to new release requirements | MSG | Vinodh | blocked | scan
QA-021 |  | QXP product page | AI features note: 'from v21.1 onwards' | Version ref | Green | Check still accurate | MSG | Vinodh | blocked | scan
QA-022 |  | QXP product page | Add-ons section: Infografix card -> infografix.app (utm productpage) | Module | Red | Remove card | Andrew OK | Vinodh | open | scan | Not raised on call
QA-023 |  | QXP product page | 'View comparison' -> content.quark.com/26_QXP_Features_Comparision_V22 | PDF asset | Yellow | Same as nav row | Q-08 | TBD | open | scan
QA-024 |  | What's New | Page title 'What's New in the Latest Version of QuarkXPress' - evergreen URL + title | Structure | Green | No change; add new block on top | MSG | Vinodh | blocked | scan | Running changelog v20 -> v22.0.1
QA-025 |  | What's New | New release block: features, images, (videos?) | Feature list | Yellow | Build from F-01 + F-03 | MSG; screenshots | Design + Vinodh | blocked | scan | Current block: 8 features, 7 with video
QA-026 |  | What's New | Hero 'Watch Video' -> youtu.be/5l54uqfpg1c | Video | Orange | Replace with new video or remove button | Q-06; F-04 | Andrew | open | call+scan | Andrew raised this button specifically
QA-027 |  | What's New | 'See Release Notes' -> /documentation/quarkxpress/2026/.../Release Notes.pdf | PDF asset | Yellow | Point to new release notes | Quark product team | TBD | blocked | scan
QA-028 |  | What's New | 'Download the What's New PDF' -> content.quark.com/QXP_2026_What's_New_v22.0.1 | PDF asset | Orange | New PDF or drop button | Q-08 | Andrew | open | scan | Someone has to make this PDF; candidate to cut
QA-029 |  | Shop | 'QuarkXPress 2026' / '2025 (v21.1)' / macOS Tahoe mentions in copy + FAQs | Year ref | Green | Swap | MSG (name) | Vinodh | blocked | scan
QA-030 |  | Shop | Buy buttons -> checkout.quark.com/1486/purl-qxp-subscription¦license ... x-source=Aprilshop&x-campaign=26AprilPromo | Commerce link | TBD | Confirm whether tag affects price; set release campaign tag | Q-10 | Vinodh | open | scan | Cleverbridge
QA-031 |  | Shop | No prices or currency control in page text | Pricing | TBD | Visual check: how do 5 currencies render | Q-05 | Vinodh | open | scan | Probably JS / Cleverbridge-injected
QA-032 |  | Shop | No upgrade SKU visible | Commerce | TBD | Locate upgrade path for EOL version holders | Q-04 | Vinodh + Andrew | open | call+scan
QA-033 |  | Renewals | 'Renew Now' + 'Purchase Lookup' -> cleverbridge.com customer portal | Commerce link | Green | No change expected; click-test | - | Vinodh | open | scan | No upgrade offer on this page
QA-034 | (campaign LPs) | Campaign landing pages | NOT INVENTORIED - old team kept one per campaign | Landing page | TBD | Inventory from Pardot email links | PARDOT | Vinodh | blocked | call | DEC-13: collapse to one page + params
QA-035 | https://www.quark.com/academic | Academic pricing | 9 hidden outbound links to unrelated third-party sites (unvi.es, condoforsalebangkok.com, kumarskitchen.com, technoservesolutions.com, mgapress.com.br, intersmartsolution.com, cvworld.in, silversea-media.my, ausfitprojects.com.au) sitting between header and content | Security | Red | Remove links; check page revisions + who edited (page modified 2025-10-20); rotate that user's password; scan site | - | Vinodh | open | scan2 | Verified by live link extraction. NOT present on 39 other pages checked incl. /de/academic. Looks like SEO link injection in this page's content | 21 Sep live fetch: STILL LIVE - all 9 links present
QA-036 | (global) | Header | Logo asset QuarkXPress_BRANDMARK_RGB_2026_v5_GRAY.webp | Brand asset | Yellow | New-year brandmark from Quark | Quark brand team | TBD | blocked | scan2 | Other pages still use 2025, 2023, 2022, 2021 brandmarks
QA-037 | (global) | Localisation | WPML 4.9.7, 7 languages (en + de, es, fr, it, ja, ko) - translated page copies, not auto-translate | Localisation | Orange | Decide: update EN only at launch, translations after? Or machine-translate the delta | Andrew | Andrew | open | scan2 | Answers Q-03. ~40-language switcher is a separate overlay widget
QA-038 | https://www.quark.com/page-layouts | Capability pages x5 | Shared block 'QuarkXPress 2026 Features' (heading + 3 in-body '2026' strings) identical on page-layouts, typography, graphics, photo-editing, digital-publishing | Feature list | Yellow | Rewrite once from F-01; check if it's one reusable block (then 1 edit) or 5 copies | MSG; F-01 | Vinodh | blocked | scan2 | Biggest single lever after the flagship pages
QA-039 | https://www.quark.com/page-layouts | Capability pages x5 | Shared licensing block (subscription vs perpetual, links to /shop) | Pricing copy | Green | No change unless licensing changes | MSG | Vinodh | open | scan2
QA-040 | https://www.quark.com/typography-fonts-and-styles-in-creative-design | Typography | 'The new AI-powered Font Pairing in QuarkXPress 2026' + video lL2RY3cUfVM (titled '...in QuarkXPress 2025' elsewhere) | Year ref | Green | Swap year; 'new' no longer true | MSG (name) | Vinodh | blocked | scan2
QA-041 | https://www.quark.com/graphics-and-illustrations | Graphics | 'Other software requires you to pay an extra $89.' (Pantone) | Claim | Orange | Verify the competitor price is still true or soften | - | Andrew | open | scan2 | Also on /6-reasons-to-switch and /brand-identity | 21 Sep live fetch: confirmed verbatim. Page modified 2025-12-08
QA-042 | https://www.quark.com/quarkxpress-trial | Trial | Meta description: '...be more productive with QuarkXPress 2021' | Year ref | Green | Rewrite meta description without a year | - | Vinodh | open | scan2 | Fix now. /quarkxpress-demo redirects here | 21 Sep live fetch: confirmed - same string is also the og:description (social share text)
QA-043 | https://www.quark.com/quarkxpress-trial | Trial | 'What's New' video youtu.be/5l54uqfpg1c + Gartner review embeds (failed to load in scrape) | Video + Reviews | Orange | Same decision as product page (Q-06, Q-07) | Q-06; Q-07 | Andrew | open | scan2 | Every page CTAs here - highest-traffic release surface after homepage. Ready-made replacement exists: see QA-070 | 21 Sep live fetch: 3 Gartner embeds on this page, all fail. Same dead host as QA-019
QA-044 | https://www.quark.com/ai-in-quarkxpress | AI in QuarkXPress | '...on QuarkXPress 2026 (v21.1), at no additional cost' - 2026 is v22; v21.1 was 2025 | Factual error | Green | Correct now: 'v21.1 onwards' | - | Vinodh | open | scan1 | From summarised fetch - eyeball before editing | 21 Sep live fetch: confirmed verbatim: 'on QuarkXPress 2026 (v21.1), at no additional cost'. Page modified 2025-11-06
QA-045 | https://www.quark.com/ai-in-quarkxpress | AI in QuarkXPress | AI allowance: '7,200 Quarky AI pages and 5,000 Font Pairing instances annually' | Spec | Yellow | Confirm allowance for new release | MSG | Vinodh | blocked | scan1 | Also on /products/quarkxpress/ai-faqs
QA-046 | https://www.quark.com/products/quarkxpress/ai-faqs | AI FAQs | Version refs: 21.1, v21.0.3, 'QuarkXPress 2026', 'QuarkXPress 2025' user guide; 'perpetual users must update to v2026' | Year ref | Yellow | Update FAQ answers for new version | MSG | Vinodh | blocked | scan1
QA-047 | https://www.quark.com/6-reasons-to-switch-to-quarkxpress | Switch page | 'QuarkXPress 2026' latest-release copy; WATCH NOW -> youtu.be/5l54uqfpg1c; buy link utm_campaign=23QXPSwitch | Year ref + Video | Green | Swap year; video per Q-06; leave UTM | MSG (name) | Vinodh | blocked | scan1
QA-048 | https://www.quark.com/quarkxpress-for-students-and-teachers | Students & teachers | 'Check out What's New in our 2026 release.' + WATCH NOW video 5l54uqfpg1c | Year ref + Video | Green | Swap year; video per Q-06 | MSG (name) | Vinodh | blocked | scan2 | Price slots render empty in scrape (JS-filled)
QA-049 | https://www.quark.com/academic | Academic pricing | 'QuarkXPress 2026' x2 in copy | Year ref | Green | Swap | MSG (name) | Vinodh | blocked | scan1
QA-050 | (commerce) | Academic / charity / government | Purchases route via federation.proxi.id (eligibility verification), not Cleverbridge directly | Commerce | TBD | Confirm nothing version-specific is configured at Proxi.id | - | Vinodh | open | scan1 | Third commerce system - not mentioned on the call
QA-051 | https://www.quark.com/qxp-government | Government | Hard-coded '$239 per year' maintenance renewal | Pricing | Yellow | Confirm price holds for new release | Quark | Andrew | open | scan1 | Only hard-coded QXP price found on the site | 21 Sep live fetch: confirmed verbatim
QA-052 | https://www.quark.com/request-previous-version | Request previous version | Version dropdown stops at QuarkXPress 2024 (no 2025); will also need 2026 after launch | Form | Green | Add 2025 now; add 2026 at launch | - | Vinodh | open | scan1 | Form submit target not visible | 21 Sep live fetch: confirmed - list runs QuarkXPress 2024 down to 7, plus CopyDesk 2023
QA-053 | https://www.quark.com/support/installers | Installers | New 'Recommended' tile for new version; demote 2026 v22.0.1; new files.quark.com hashes + utm_content | Release asset | Yellow | Build at launch; needs installer files from Quark product team | Quark product team | Vinodh | blocked | scan2 | Launch-day critical: trial + buyers land here
QA-054 | https://www.quark.com/support/installers | Installers | Existing defects: wrong alt text on 5 updaters, utm_content mismatches (21.1.2 tagged v21.1; June/May tagged v21.0.3), CopyDesk 2024 alt says 2022, Quark Update alt says 2.2.3, two file_url values start with %20, no 21.1.2 updater | Defect | Green | Fix in the same pass | - | Vinodh | open | scan2
QA-055 | https://www.quark.com/support/documentation/quarkxpress/ | Documentation index | Needs new version tile; page is noindex,nofollow | Release asset | Yellow | Add tile at launch | Quark product team (docs) | Vinodh | blocked | scan2
QA-056 | https://www.quark.com/support/documentation/quarkxpress/quarkxpress-2026 | Documentation 2026 | Clone for new version. Current page cross-links to 2019/2021/2023 docs, an http:// 2019 PDF, a '2025' key-commands file in the 2026 folder | Release asset | Yellow | Clone + relink at launch; docs come from Quark | Quark product team (docs) | Vinodh | blocked | scan2
QA-057 | https://www.quark.com/quarkxpress-tutorials | Tutorials | 66 videos, titles mix 2024 / 2025 / 2026; KB link points to legacy quarkportal.force.com | Video index | Orange | Leave titles (historic); fix KB link now; add new-release tutorials only if Quark makes them | - | Vinodh | open | scan2 | Same legacy KB link on /solutions/quarkxpress-support-hub
QA-058 | https://www.quark.com/quarkxpress-training | Training | Promotes Udemy course + workbook 'QuarkXPress 2025: The Essentials & Beyond' | Third-party | Orange | Leave; note it's two versions behind after launch | - | Andrew | open | scan2
QA-059 | https://www.quark.com/quarkxpress-webinar-series | Webinar series | October 2021 webinars; Zoom registration links still live | Dead page | Red | Unpublish / redirect to /quarkxpress-tutorials | Andrew OK | Vinodh | open | scan2 | 5 years stale
QA-060 | https://www.quark.com/qxpcontest | Splash-screen contest | 2023 contest; 2023 brandmark; 'upcoming release' wording; meta says 'Enter now' | Dead page | Red | Unpublish / redirect | Andrew OK | Vinodh | open | scan2
QA-061 | https://www.quark.com/choose-how-you-buy-complete | Campaign completion page | 'QuarkXPress 2024 Features', qxp24 logo, modified 2024-10-04, broken og:description | Dead page | Orange | Check if any live form still lands here; if not, retire. If yes, update block | - | Vinodh | open | scan2 | Pair: /choose-how-you-buy-thankyou
QA-062 | https://www.quark.com/pinterest-campaign | Pinterest promo LP | 10% off subscription / 20% off perpetual; 4 checkout.quark.com links with x-source=mspublisher(affiliate) + audience IDs | Landing page | Orange | Is this promo still meant to run through a new release? Decide keep/pause | Andrew | Andrew | open | scan2 | Only live discount LP found. Modified 2026-04-09. A template for DEC-13's single LP
QA-063 | https://www.quark.com/solutions/quarkxpress-support-hub | Support hub | Maintenance wording: 'entitled to the latest version', 'previously called an Advantage Plan', a QuarkXPress 2020 upgrade example; shop.quark.com + qxpsales@quark.com links; modified 2024-10-28 | Upgrade path | Yellow | Closest thing on the site to an upgrade explanation - read before writing upgrade email | Q-04 | Andrew | open | scan2 | Partly answers Q-04: upgrades appear to be sold as maintenance, via Cleverbridge / sales email
QA-064 | https://www.quark.com/products/quarkxpress-copydesk | CopyDesk | 2021/22 data sheet, 2024 v20.1.1 system reqs (installers offer 2025 v21.1.2), 2021 artwork | Stale page | Orange | Out of release scope unless CopyDesk ships too - ask | MSG | Andrew | open | scan2
QA-065 | https://www.quark.com/join-the-affiliate-program | Affiliate | Malformed CJ signup URL (second '?'); 2025 brandmark | Defect | Green | Fix URL | - | Vinodh | open | scan2 | Low priority | 21 Sep live fetch: confirmed - 'Get Started' button URL has a second '?' (cid=5620604?utm_source=...). Second CTA on the page is fine
QA-066 | https://www.quark.com/about/news | News | Every past release has a press release (2022, 2023, 2024, 2024 spring, 2025, 2025 spring, 2026) | Release asset | Yellow | New press release - who writes it? | MSG | Andrew | open | map | Not raised on the call
QA-067 | https://www.quark.com/about/blog | Blog | Past releases have 1-2 launch blog posts ('QuarkXPress 2026 is here and ready for macOS Tahoe', 'Variable fonts is here...') | Release asset | Yellow | Launch blog post from F-01 | MSG | Andrew | open | map | Not raised on the call. Old posts stay as-is
QA-068 | https://www.quark.com/brochure-layout-design | Use-case pages x5 | No year refs in copy (brochure, book, magazine, newspaper, brand identity). 2024-named image assets only. Copy slips: newspaper page says 'book', brand page has a 'Magazine Layout' heading | Evergreen | Green | No release change. Fix the two copy slips when convenient | - | Vinodh | open | scan2 | Good news: 5 pages off the list
QA-069 | https://www.quark.com/request-previous-version | Request previous version | Heading 'Explore the Latest Features in QXP 2026' + video youtu.be/M8FewBUzE1s - a second what's-new video, different from 5l54uqfpg1c used everywhere else | Year ref + Video | Green | Swap heading; video per Q-06. Check which of the two videos is the current one | MSG (name); Q-06 | Vinodh | blocked | scan3 | Found during the live check | 21 Sep live fetch: found
QA-070 | https://www.quark.com/request-previous-version | Request previous version | Reviews shown as three plain-text Capterra 2025 quotes (Pete C, Luke D, Melinda E) - no iframe, loads fine | Reviews | Green | Reuse this block on the product and trial pages in place of the dead Gartner embeds | Q-07 | Andrew | open | scan3 | Answers Q-07 without new content: the site already has a working reviews pattern | 21 Sep live fetch: found
QA-071 | https://www.quark.com/ai-in-quarkxpress | AI in QuarkXPress | 'available in QuarkXPress 2026!' and 'The new AI-powered Font Pairing in QuarkXPress 2026' - two year refs the first scan missed | Year ref | Green | Swap year; 'new' no longer true for Font Pairing | MSG (name) | Vinodh | blocked | scan3 | Same Font Pairing sentence as QA-040 | 21 Sep live fetch: found